## Sheet1
Task | Task Name | Start Date | Duration | End Date
1 | Learn Backbone and API | March 19th | 7 | March 26th
2 | Create basic working application | march 27th | 1 | march 28th
3 | Create API-less skeleton | march 29th | 7 | april 5th
4 | Create API-less skeleton application | april 6th | 9 | april 15th
5 | Add Basic Api Support | april 14th | 4 | april 18t
6 | Add additional api support | april 19th | 7 | april 25th
7 | Polish and test | april 25th | 21 | may 15th